BURNLEY NC- Greener Houses Retrofit Planning Process – “The Nuts and Bolts”

1. Discovering the Strengths, Weaknesses & Issues that impact sustainability at BNC

Gathering the Evidence: What information do we have already? What information do we still need to collect?

|  | 1. Discovering - Process to be concluded by Wednesday March 31 |
| --- | --- |
| STATUS | Objectives: Collect all data into a central file – hardcopy & group webpage - Jeff Capture and define remaining data we need to define problems - Jeff Fill in information gaps we have in existing data - Jeff Tasks Completed: 85% complete See Checklist for Retrofit Design Plan Tasks to be Done: See Checklist for Retrofit Design Plan NOTES – Meeting on Wed. March 24 to conclude process |

2. Defining the Strengths, Weaknesses & Issues that impact sustainability at BNC

Describing Problems: What are the problems? Where are the problems? Why are they problems?

|  | 2. Defining - Process to be concluded by Wednesday April 28 |
| --- | --- |
| STATUS | Objectives: Analyse data and summarize the findings for the group; Identify/quantify current performance (ie Nikki’s piechart) – Trevor/Jeff Define and agree on general problem areas of House based on templates and other information collected - Jeff Define specific problems – where, what, when, who, why (rooms, activities, behaviour, appliances, equipment, etc…) and layout problem statements – Jeff/Trevor Fill-in House/Site Map with ESD, locations of fittings, external impacts, etc - Jeff Ranking problems in order of priority based on overall impact on House sustainability - Jeff Tasks Completed: Some general agreement about source of major problems; List of general problem – too vague Tasks to be Done: Pie chart; List of specific problems; Mapping of BNC ESD/etc…; Ranked list of problems How: In workshop format as a group discussion on Wed. March 24, follow up individuals working on tasks if needed Who: Grant/Kerstin – Pie Chart; Problem lists/rankings – All; Mapping exercise – All; NOTES – Will have done Water, First Rate and Lighting |

3. Addressing Weaknesses & Issues that impact sustainability at BNC

Proposing and Researching retrofit options to effectively deal with problems

|  | 3. Addressing - Process to be concluded by Wednesday May 12 |
| --- | --- |
| STATUS | Objective: Lay out decision-making framework & criteria – Trevor/Jeff Propose and explore list of potential solution options for each problem defined – Trevor/Jeff Research potential solution options; organize options into topics and split research tasks amongst houses - Jeff Investigate and complete Research Template for each specific potential solutions - Jeff Tasks Completed: Some general solution options have been proposed and researched Tasks to be Done: All the above How: Group discussion of decision-making framework & criteria; Individuals research options with help of Jika Vols/ATA/Etc… Who: All, especially: Grant, Kerstin, Helen, Jemma, Virginia, Chris; NOTES - |

4. Deciding what solutions will be put into the finalized Retrofit Plan for BNC

Deciding on appropriate retrofit options and presenting to Volunteers, Trevor, GH Staff, other Stakeholders

|  | 4. Deciding - Process to be concluded by Wednesday June 9 |
| --- | --- |
| STATUS | Objective: Present findings of research to volunteer group, indicate how each solution stacks up against overall project criteria – Trevor/Jeff Decide on specific solutions (product/material) to be included in the retrofit plan – Trevor/Jeff Rank each solution against each other to determine which has priority based on cost/project criteria/feasibility – Trevor/J Prioritize the order in which specific items should be purchased and installed – Trevor/Jeff Investigate sourcing of products and donation/bulk buying/sponsorship/etc… schemes – Linda/Trevor Tasks Completed: None Tasks to be Done: All How: Volunteers present findings to group; Discussion and CD activity to facilitate decision process & ranking of solutions process Who: Everyone NOTES – Will have done Renewable Energy & Green Purchasing Workshops |

5. Presenting the finalized Retrofit Plan for BNC for Yarra Council approval

|  | 5. Presenting - Process to be concluded by Wednesday June 30 |
| --- | --- |
| STATUS | Objective: Format retrofit plan based on Council’s criteria and protocol – Linda/Jeff Decide which volunteers will present the retrofit plan – Linda/Jeff Train the volunteer presenter if needed Tasks Completed: Tasks to be Done: How: Who: NOTES - |

************************************************************************************************************************

JIKA CC- Greener Houses Retrofit Planning Process – “The Nuts and Bolts”

1. Discovering the Strengths, Weaknesses & Issues that impact sustainability at JCC

Gathering the Evidence: What information do we have already? What information do we still need to collect?

|  | 1. Discovering - Process to be concluded by Wednesday March 31 |
| --- | --- |
| STATUS | Objectives: Collect all data into a central file – hardcopy & group webpage - Jeff Capture and define remaining data we need to define problems - Jeff Fill in information gaps we have in existing data - Jeff State of Play: See Checklist for Retrofit Design Plan Tasks to be Done: See Checklist for Retrofit Design Plan NOTES - Meeting on Thurs. March 25 to conclude process |

2. Defining the Strengths, Weaknesses & Issues that impact sustainability at JCC

Describing Problems: What are the problems? Where are the problems? Why are they problems?

|  | 2. Defining - Process to be concluded by Wednesday April 28 |
| --- | --- |
| STATUS | Objectives: Analyse data and summarize the findings for the group; Identify/quantify current performance - Jeff Define and agree on general problem areas of House based on templates and other information collected – Linda/Jeff Define specific problems – where, what, when, who, why (rooms, activities, behaviour, appliances, equipment, etc…) and layout problem statements – Linda/Jeff Fill-in House/Site Map with ESD, locations of fittings, external impacts, etc - Jeff Ranking problems in order of priority based on overall impact on House sustainability State of Play: Created pie chart/comparisons; Have generated a general and specific list of problems; Have begun prioritizing Tasks to be Done: Define problems more precisely; Mapping of JCC ESD/etc… ; Confirm ranking of problems How: Workshop w/ Trevor to define problems and map ESD Who: All volunteers NOTES – Trevor to meet on Wed. March 25 to help sort out Defining Process |

3. Addressing Weaknesses & Issues that impact sustainability at JCC

Proposing and Researching retrofit options to effectively deal with problems

|  | 3. Addressing - Process to be concluded by Wednesday May 12 |
| --- | --- |
| STATUS | Objective: Lay out decision-making framework & criteria – Trevor on March 25 Propose and explore list of potential solution options for each problem defined – Jeff/Trevor Research potential solution options; organize options into topics and split research tasks amongst houses - Jeff Investigate and complete Research Template for each specific potential solutions - Jeff State of Play: Developed initial criteria; Proposed a very general list of options; Began researching solutions Tasks to be Done: Firm up criteria; Get specific about options/products; Complete research templates; How: Workshop; Consensus approach/CD process Who: All volunteers NOTES - Trevor to meet on Wed. March 25 to help sort out Decision making framework & Criteria |

4. Deciding what solutions will be put into the finalized Retrofit Plan for JCC

Deciding on appropriate retrofit options and presenting to Volunteers, Trevor, GH Staff, other Stakeholders

|  | 4. Deciding - Process to be concluded by Wednesday June 9 |
| --- | --- |
| STATUS | Objective: Present findings of research to volunteer group, indicate how each solution stacks up against overall project criteria - Trev Group decides on specific solutions (product/material) to be included in the retrofit plan – Trevor/Jeff Group prioritizes the order in which specific items should be purchased and installed – Trevor/Jeff Group investigates sourcing of products and donation/bulk buying/sponsorship/etc… schemes – Linda/Trevor State of Play: Not yet Tasks to be Done: All How: Vols present info to group; Group consensus Who: NOTES - |

5. Presenting the finalized Retrofit Plan for JCC for Darebin Council approval

|  | 5. Presenting - Process to be concluded by Wednesday June 30 |
| --- | --- |
| STATUS | Objective: Format retrofit plan based on Council’s criteria and protocol - Linda Decide which volunteers will present the retrofit plan – Linda/Jeff Train the volunteer presenter if needed Tasks Completed: Not yet Tasks to be Done: How: Who: NOTES - |

************************************************************************************************************************

WATSONIA - Greener Houses Retrofit Planning Process – “The Nuts and Bolts”

1. Discovering the Strengths, Weaknesses & Issues that impact sustainability at WNH

Gathering the Evidence: What information do we have already? What information do we still need to collect?

|  | 1. Discovering - Process to be concluded by Wednesday March 31 |
| --- | --- |
| STATUS | Objectives: Collect all data into a central file – hardcopy & group webpage Capture and define remaining data we need to define problems - Fill in information gaps we have in existing data Tasks Completed: See Checklist for Retrofit Design Plan Tasks to be Done: See Checklist for Retrofit Design Plan NOTES - |

2. Defining the Strengths, Weaknesses & Issues that impact sustainability at WNH

Describing Problems: What are the problems? Where are the problems? Why are they problems?

|  | 2. Defining - Process to be concluded by Wednesday April 28 |
| --- | --- |
| STATUS | Objectives: Analyse data and summarize the findings for the group; Identify/quantify current performance (ie Nikki’s piechart) Define and agree on general problem areas of House based on templates and other information collected Define specific problems – where, what, when, who, why (rooms, activities, behaviour, appliances, equipment, etc…) and layout problem statements Fill-in House/Site Map with ESD, locations of fittings, external impacts, etc Ranking problems in order of priority based on overall impact on House sustainability Tasks Completed: Tasks to be Done: How: Who: NOTES - |

3. Addressing Weaknesses & Issues that impact sustainability at WNH

Proposing and Researching retrofit options to effectively deal with problems

|  | 3. Addressing - Process to be concluded by Wednesday May 12 |
| --- | --- |
| STATUS | Objective: Lay out decision-making framework & criteria Propose and explore list of potential solution options for each problem defined Research potential solution options; organize options into topics and split research tasks amongst houses Investigate and complete Research Template for each specific potential solutions Tasks Completed: Tasks to be Done: How: Who: NOTES - |

4. Deciding what solutions will be put into the finalized Retrofit Plan for WNH

Deciding on appropriate retrofit options and presenting to Volunteers, Trevor, GH Staff, other Stakeholders

|  | 4. Deciding - Process to be concluded by Wednesday June 9 |
| --- | --- |
| STATUS | Objective: Present findings of research to volunteer group, indicate how each solution stacks up against overall project criteria Group decides on specific solutions (product/material) to be included in the retrofit plan Group prioritizes the order in which specific items should be purchased and installed Group investigates sourcing of products and donation/bulk buying/sponsorship/etc… schemes Tasks Completed: Tasks to be Done: How: Who: NOTES - |

5. Presenting the finalized Retrofit Plan for WNH for Banyule Council approval

|  | 5. Presenting - Process to be concluded by Wednesday June 30 |
| --- | --- |
| STATUS | Objective: Format retrofit plan based on Council’s criteria and protocol Tasks Completed: Tasks to be Done: How: Who: NOTES - |

************************************************************************************************************************

ALLWOOD NH - Greener Houses Retrofit Planning Process – “The Nuts and Bolts”

1. Discovering the Strengths, Weaknesses & Issues that impact sustainability at ANH

Gathering the Evidence: What information do we have already? What information do we still need to collect?

|  | 1. Discovering - Process to be concluded by Wednesday March 31 |
| --- | --- |
| STATUS | Objectives: Collect all data into a central file – hardcopy & group webpage Capture and define remaining data we need to define problems - Fill in information gaps we have in existing data Tasks Completed: See Checklist for Retrofit Design Plan Tasks to be Done: See Checklist for Retrofit Design Plan NOTES - |

2. Defining the Strengths, Weaknesses & Issues that impact sustainability at ANH

Describing Problems: What are the problems? Where are the problems? Why are they problems?

|  | 2. Defining - Process to be concluded by Wednesday April 28 |
| --- | --- |
| STATUS | Objectives: Analyse data and summarize the findings for the group; Identify/quantify current performance (ie Nikki’s piechart) Define and agree on general problem areas of House based on templates and other information collected Define specific problems – where, what, when, who, why (rooms, activities, behaviour, appliances, equipment, etc…) and layout problem statements Fill-in House/Site Map with ESD, locations of fittings, external impacts, etc Ranking problems in order of priority based on overall impact on House sustainability Tasks Completed: Tasks to be Done: How: Who: NOTES - |

3. Addressing Weaknesses & Issues that impact sustainability at ANH

Proposing and Researching retrofit options to effectively deal with problems

|  | 3. Addressing - Process to be concluded by Wednesday May 12 |
| --- | --- |
| STATUS | Objective: Lay out decision-making framework & criteria Propose and explore list of potential solution options for each problem defined Research potential solution options; organize options into topics and split research tasks amongst houses Investigate and complete Research Template for each specific potential solutions Tasks Completed: Tasks to be Done: How: Who: NOTES - |

4. Deciding what solutions will be put into the finalized Retrofit Plan for ANH

Deciding on appropriate retrofit options and presenting to Volunteers, Trevor, GH Staff, other Stakeholders

|  | 4. Deciding - Process to be concluded by Wednesday June 9 |
| --- | --- |
| STATUS | Objective: Present findings of research to volunteer group, indicate how each solution stacks up against overall project criteria Group decides on specific solutions (product/material) to be included in the retrofit plan Group prioritizes the order in which specific items should be purchased and installed Group investigates sourcing of products and donation/bulk buying/sponsorship/etc… schemes Tasks Completed: Tasks to be Done: How: Who: NOTES - |

5. Presenting the finalized Retrofit Plan for ANH for Nillumbik Council approval

|  | 5. Presenting - Process to be concluded by Wednesday June 30 |
| --- | --- |
| STATUS | Objective: Format retrofit plan based on Council’s criteria and protocol Tasks Completed: Tasks to be Done: How: Who: NOTES - |

************************************************************************************************************************